## Test Plan
Test Cases | Test Schedule | Assigned Tester | Date of Execution | Status | Bug IDs
Authetication
AUTH-0001: Authentication testing - Account Sign Up and Registration | 2026-04-08 | slpyMryll | 2026-06-04 | PASSED
AUTH-0002: Authentication testing - Account Sign Up and Registration | 2026-04-08 | slpyMryll | 2026-06-04 | PASSED
AUTH-0003: Authentication testing - Form Fields & Validation | 2026-04-08 | slpyMryll | 2026-06-04 | FAILED | BUG-0001
AUTH-0004: Authentication testing - Form Fields & Validation | 2026-04-08 | slpyMryll | 2026-06-04 | PASSED
AUTH-0005: Authentication testing - Email Verification / Activation | 2026-04-08 | slpyMryll | 2026-06-04 | PASSED
AUTH-0006: Authentication testing -Email Verification / Activation | 2026-04-08 | slpyMryll | 2026-06-04 | PASSED
Commission Request Testing
COMM-0001: Commission Request Testing - Commissioner Opens Post Request Modal | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
COMM-0002: Commission Request Testing - Commissioner Posts Open Request | 2026-04-08 | slpyMryll | 2026-06-06 | FAILED | BUG-005
COMM-0003: Commission Request Testing -Artist Test Account Setup | 2026-04-08 | slpyMryll | 2026-06-06 | FAILED | BUG-006
COMM-0004: Commission Request Testing - Artist Sends Commission Offer | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
COMM-0005: Commission Request Testing - Commissioner Reviews Incoming Offers | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
COMM-0006: Commission Request Testing - Commissioner Hires Artist | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
CommunicationTesting
MSG-0001: Communication Testing - Inbox Empty State Rendering | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
MSG-0002: Communication Testing - Inbox Search Field Availability | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
MSG-0003: Communication Testing -Inbox Conversation Search Handling | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
MSG-0004: Communication Testing -Conversation Initialization Prompt | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
MSG-0005: Communication Testing - Message Sending Procedure | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
MSG-0006: Communication Testing - Top Artist Sidebar Messaging Option | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
MSG-0007: Communication Testing - Inbox Incoming Message Rendering | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
MSG-0008: Communication Testing - Inbox Incoming Message Rendering | 2026-04-08 | slpyMryll | 2026-06-06 | PASSED
Discovery and Navigation Testing
SRCH-001: Discovery and Navigation Testing - Global Text Search | 2026-04-08 | slpyMryll | 2026-06-04 | PASSED
SRCH-002: Discovery and Navigation Testing - Dynamic Filter Tags | 2026-04-08 | slpyMryll | 2026-06-04 | PASSED
SRCH-003: Discovery and Navigation Testing - Interactive Result Cards | 2026-04-08 | slpyMryll | 2026-06-04 | FAILED | BUG-0002
SRCH-003: Discovery and Navigation Testing - Interactive Result Cards | 2026-04-08 | slpyMryll | 2026-06-04 | FAILED | BUG-0003
Financials Testing
PAY-0001: Financials Testing - Marketplace Add to Cart | 2026-04-08 | eking723 | 2026-06-10 | PASSED
PAY-0002: Financials Testing - Shopping Cart Page Display | 2026-04-08 | eking723 | 2026-06-10 | PASSED
PAY-0003: Financials Testing - Selective Checkout Item Selection | 2026-04-08 | eking723 | 2026-06-10 | PASSED
PAY-0004: Financials Testing - Cart Quantity Controls | 2026-04-08 | eking723 | 2026-06-10 | PASSED
PAY-0005: Financials Testing - Cart Item Removal and Empty State | 2026-04-08 | eking723 | 2026-06-10 | PASSED
PAY-0006: Financials Testing - Checkout Disabled With No Selection | 2026-04-08 | eking723 | 2026-06-10 | PASSED
PAY-0007: Financials Testing - PayMongo Checkout Session Initialization | 2026-04-08 | eking723 | 2026-06-10 | PASSED
PAY-0008: Financials Testing - PayMongo Paid Webhook Order Commit | 2026-04-08 | eking723 | 2026-06-10 | PASSED
PAY-0009: Financials Testing - Commission Deposit Checkout Initialization | 2026-04-08 | eking723 | 2026-06-10 | PASSED
PAY-0010: Financials Testing - Commission Deposit Paid Commit | 2026-04-08 | eking723 | 2026-06-10 | NOT RUN | BUG-007
PAY-0011: Financials Testing - Artist Marks Commission Ready for Final Payment | 2026-04-08 | eking723 | 2026-06-10 | NOT RUN | BUG-007
PAY-0012: Financials Testing - Commission Final Payment Commit | 2026-04-08 | eking723 | 2026-06-10 | NOT RUN | BUG-007
Marketplace Testing
MKT-0001: Marketplace Testing - Art Catalog Browsing & Search | 2026-04-08 | eking723 | 2026-06-10 | PASSED
MKT-0002: Marketplace testing - Price/Buy Controls | 2026-04-08 | eking723 | 2026-06-10 | PASSED
MKT-0003: Marketplace testing - Ask Artist Availability | 2026-04-08 | eking723 | 2026-06-10 | PASSED
Profile Management Testing
PRF-0001: Profile Management testing - Profile Display | 2026-04-01 | slpyMryll | 2026-06-06 | PASSED
PRF-0002: Profile Management testing -Profile Display | 2026-04-01 | slpyMryll | 2026-06-06 | FAILED | BUG-004
PRF-0003: Profile Management testing -Edit Profile | 2026-04-01 | slpyMryll | 2026-06-06 | PASSED
PRF-0004: Profile Management testing - Edit Profile | 2026-04-01 | slpyMryll | 2026-06-06 | PASSED
PRF-0005: Profile Management testing - Account Type Handling | 2026-04-01 | slpyMryll | 2026-06-06 | PASSED
PRF-0006: Profile Management testing - Recent Activity Logging | 2026-04-01 | slpyMryll | 2026-06-06 | PASSED
PRF-0007: Profile Management testing -Recent Activity Logging | 2026-04-01 | slpyMryll | 2026-06-06 | PASSED
PRF-0008: Profile Management testing - Become a Seller | 2026-04-01 | slpyMryll | 2026-06-06 | PASSED
PRF-0009: Profile Management testing - Become a Seller | 2026-04-01 | slpyMryll | 2026-06-06 | PASSED
Reputation Testing
REV-0001: Reputation Testing - Rating Score & Visibility | 2026-04-01 | slpyMryll | 2026-06-10 | PASSED
REV-0002: Reputation Testing - Rating Score & Visibility | 2026-04-01 | slpyMryll | 2026-06-10 | PASSED
REV-0003: Reputation Testing - Rating Score & Visibility | 2026-04-01 | slpyMryll | 2026-06-10 | PASSED
REV-0004: Reputation Testing - Rating Metadata Stability | 2026-04-01 | slpyMryll | 2026-06-10 | PASSED
REV-0005: Reputation Testing -Rating Metadata Stability | 2026-04-01 | slpyMryll | 2026-06-10 | PASSED
Social and Community Testing
FEED-001: Social and Community Testing - Artwork Publication | 2026-04-01 | slpyMryll | 2026-06-10 | PASSED
FEED-002: Social and Community Testing - Artwork Publication | 2026-04-01 | slpyMryll | 2026-06-10 | PASSED
FEED-003: Social and Community Testing - Reaction Handlers | 2026-04-01 | slpyMryll | 2026-06-10 | PASSED
FEED-004: Social and Community Testing - Social Interaction Hooks | 2026-04-01 | slpyMryll | 2026-06-10 | PASSED
FEED-005: Social and Community Testing - Social Interaction Hooks | 2026-04-01 | slpyMryll | 2026-06-10 | PASSED
FEED-006: Social and Community Testing - Social Interaction Hooks | 2026-04-01 | slpyMryll | 2026-06-10 | PASSED

## Reports
Total Test Cases | 59
Passed Test Cases | 50
Failed Test Cases | 6
Execution Completion | 56
Execution Completion (%) | 94.92%